## Defect Planning and Tracking
Week	Nov 11	Nov 18	Nov 25	Dec 02	Dec 09	Dec 16	Dec 23	Dec 30	Jan 06	Jan 13	Jan 20	Jan 27
Opened	1	2	0	1
Closed	9	2	2	7
Not Closed	9	6	4	2
Not Closed – Proj	10	10	9	9	8	8	7	7	6	6	6	5

Dates / Number of Defects

## Defect Monitoring
Week	Nov 11	Nov 17	Nov 25	Dec 02	Dec 09	Dec 16	Dec 23
OPEN	16	15	16	14
FIXEDAWAITINGTEST	5	3	2	1
REJECTED	4	4	4	1
CLOSED	293	295	300	307

Dates / Number of Defects